## ETH F
Total cost / milestome
Milestone 1 | Team | cost per hour | hours | Milestone 2 | Team | cost per hour | hours | Milestone 3 | Team | cost per hour | hours | Milestone 4 | Team | cost per hour | hours | Milestone 5 | Team | cost per hour | hours | M1 | M2 | M3 | M4 | M5 | Total
(Tech work) | 8 | 44.2308 | 434 | (MVP coursework prep) | 3 |  | 155 | (Starting the MVP coursework) | 2 |  | 36 | (workshops and P2P sessions w. experts) | 4 | 64.5 | 46 | (final selection and publishing the coursework) | 4 | 56.25 | 96 | 21040 | 8410 | 2040 | 2950 | 5400 | 39840 | Hourly cost per position
Well-defined scope of work | Tokenengineer | 70 | 80 | Month 0: |  |  |  | Month 1: |  |  |  | Month 2: |  |  |  | Month 3: |  |  |  | 5600 | 0 | 0 | 0 | 0 | 5600 | PM | 35
| PM | 35 | 40 | Social media communication and announcement | Communication specialist | 40 | 10 | Workshop #1 - kick-off & MVV | Tokenengineer | 70 | 6 | Workshop #4 - Recognize Beneficiaries | Tokenengineer | 70 | 6 | Presentations #1 - Initial Design | Tokenengineer | 70 | 4 | 1400 | 400 | 420 | 420 | 280 | 2920 | Analyst | 30
Designing the user flow | Tokenengineer | 70 | 60 | Project communication and sign-up, laying the groundwork | Communication specialist | 40 | 12 |  | Advisor (Griff Green) | 80 | 2 |  | Advisor (Griff Green) | 80 | 2 |  | Advisor (Griff Green) | 80 | 4 | 4200 | 480 | 160 | 160 | 320 | 5320 | Designer | 35
| PM | 35 | 50 |  | DAO coordinator | 35 | 8 | Workshop #2 - Mapping the Territory | DAO coordinator | 35 | 16 | Workshop #5 - Maintaining Engagement | Communication specialist | 40 | 4 |  | Communication specialist | 40 | 4 | 1750 | 280 | 560 | 160 | 160 | 2910 | Frontend Dev | 45
Coordination with (Gitcoin) Passport team | PM | 35 | 16 | Launching (MVP) reputation tokens with nonprofits | Tokenengineer | 70 | 50 |  | Advisor (Griff Green) | 80 | 4 |  | Advisor (Griff Green) | 80 | 2 |  | DAO coordinator | 35 | 4 | 560 | 3500 | 320 | 160 | 140 | 4680 | Backend Dev | 60
| DAO coordinator | 35 | 10 |  | Advisor (Griff Green) | 80 | 25 | Workshop #3 - Recognize Past Capital, Labor & Expertise | Tokenengineer | 70 | 6 | Workshop #6 - Reward Systems | Tokenengineer | 70 | 13 | 1:1 Sessions - With Us & P2P | Tokenengineer | 70 | 16 | 350 | 2000 | 420 | 910 | 1120 | 4800 | Tester / QA specialist | 25
Writing the copy for the website | Communication specialist | 40 | 2 |  | DAO coordinator | 35 | 50 |  | Advisor (Griff Green) | 80 | 2 |  | Advisor (Griff Green) | 80 | 3 |  | Advisor (Griff Green) | 80 | 16 | 80 | 1750 | 160 | 240 | 1280 | 3510 | DevOps Enineer | 50
Front-end development | Frontend Dev | 45 | 60 | [8 empty] | 1:1 Sessions - With Us & P2P | Tokenengineer | 70 | 4 |  | Communication specialist | 40 | 16 | 2700 | 0 | 0 | 280 | 640 | 3620 | Communication specialist | 40
Smart contract factory deployment and integration | DevOps Enineer | 50 | 40 | [9 empty] | Advisor (Griff Green) | 80 | 4 |  | DAO coordinator | 35 | 16 | 2000 | 0 | 0 | 320 | 560 | 2880 | DAO coordinator | 35
Test on staging | Tester / QA specialist | 25 | 40 | [9 empty] | Communication specialist | 40 | 4 | Presentations #2 - Final Design | Tokenengineer | 70 | 4 | 1000 | 0 | 0 | 160 | 280 | 1440 | Tokenengineer | 70
Create the documentation | PM | 35 | 24 | [9 empty] | DAO coordinator | 35 | 4 |  | Advisor (Griff Green) | 80 | 4 | 840 | 0 | 0 | 140 | 320 | 1300 | Advisor (Griff Green) | 80
Deploy Passport and the token deployer on giveth.io | Backend Dev | 60 | 4 | [13 empty] | Communication specialist | 40 | 4 | 240 | 0 | 0 | 0 | 160 | 400
Marketing and communication | Communication specialist | 40 | 8 | [13 empty] | DAO coordinator | 35 | 4 | 320 | 0 | 0 | 0 | 140 | 460
(DAO Framework) |  | 45 | 190 |  |  |  |  | Office hours, videographing, support | 2 | 55 | 81 | Office hours, videographing, support | 2 | 55 | 85 | Post-coursework & website launch w. the complete course module |  | 43.1818 | 1345 | 10700 | 0 | 5940 | 6100 | 55350 | 78090
(R&D) identifying the tech needed for fund management for DAO’s projects on Giveth | Tokenengineer | 70 | 120 |  |  |  |  | Open office hours | Communication specialist | 40 | 9 | Open office hours | Communication specialist | 40 | 9 | Open office hours | Communication specialist | 40 | 9 | 8400 | 0 | 360 | 360 | 360 | 9480
| DAO coordinator | 35 | 40 |  |  |  |  | Running the course for future publications | Communication specialist | 40 | 12 | Running the course for future publications | Communication specialist | 40 | 16 | Running the course for future publications | Communication specialist | 40 | 16 | 1400 | 0 | 480 | 640 | 640 | 3160
| Analyst | 30 | 30 |  |  |  |  | Inviting experts to participate in the Beta training course program | examples:Zakku from Coordinape, Michael Zargham & Jeff Emmett from Blockscience | 85 | 60 | Inviting experts to participate in the Beta training course program | examples:Zakku from Coordinape, Michael Zargham & Jeff Emmett from Blockscience | 85 | 60 | Inviting experts to participate in the Beta training course program | examples:Zakku from Coordinape, Michael Zargham & Jeff Emmett from Blockscience | 85 | 60 | 900 | 0 | 5100 | 5100 | 5100 | 16200
[16 empty] | Designing the video training course with the subjects covered and publishing it for everyone to use free of charge | Communication specialist | 40 | 120 | 0 | 0 | 0 | 0 | 4800 | 4800
[17 empty] | DAO coordinator | 35 | 50 | 0 | 0 | 0 | 0 | 1750 | 1750
[17 empty] | PM | 35 | 200 | 0 | 0 | 0 | 0 | 7000 | 7000
[16 empty] | Coding, designing and Launching the website | Designer | 35 | 120 | 0 | 0 | 0 | 0 | 4200 | 4200
[17 empty] | Frontend Dev | 45 | 200 | 0 | 0 | 0 | 0 | 9000 | 9000
[17 empty] | Backend Dev | 60 | 150 | 0 | 0 | 0 | 0 | 9000 | 9000
[17 empty] | PM | 35 | 300 | 0 | 0 | 0 | 0 | 10500 | 10500
[17 empty] | Tester / QA specialist | 25 | 120 | 0 | 0 | 0 | 0 | 3000 | 3000
TOTAL |  |  | 624 |  |  |  | 155 |  |  |  | 117 |  |  |  | 131 |  |  |  | 1441 | 31740 | 8410 | 7980 | 9050 | 60750 | 117930